## Sheet1
Yearly Plan | Week | Backend | Frontend | Propose Difficulty 1-3 (1 easy and 3 is tough)
1st Quarter | 2021-01-18 | [BatchStatusApi] -Build Scaffolding project | Build Scaffolding project for Bulk Activation Tool | 1
| 2021-01-25 | [BatchStatusApi] -Test Continuous Integration | Test Continuous Integration | 2
| 2021-02-01 | [BatchStatusApi] -API that returns no data | Connects to an API | 1
| 2021-02-08 | [BatchStatusApi] -Test Continuous Delivery | Test Continuous Delivery | 2
| 2021-02-15 | [BatchStatusApi] -Documentation | Documentation | 1
| 2021-02-22 | [BatchStatusApi] -Develop Create Batch Endpoint | Add Health Check | 1
| 2021-03-01 | [BatchStatusApi] -Develop Get Batch Endpoint | Integrate with Create Batch Endpoint | 2
| 2021-03-08 | [BatchStatusApi] -Develop Delete Batch Endpoint | Integrate with Get Batch Endpoint | 2
| 2021-03-15 | [BatchStatusApi] -Develop Update Batch Endpoint | Integrate with Delete Batch Endpoint | 2
| 2021-03-22 | [BatchStatusApi] -Create Test plans | Integrate with Update Batch Endpoint | 2
| 2021-03-29 | [BatchStatusApi] -Logging | Create Test plans | 1
2nd Quarter | 2021-04-05 | [BatchStatusApi] -Backend ready for QA | Front end ready for QA | 1
| 2021-04-12 | [ActivationIntakeApi] -Build Scaffolding project |  | 1
| 2021-04-19 | [ActivationIntakeApi] -Test Continuous Integration |  | 2
| 2021-04-26 | [ActivationIntakeApi] -API that returns no data |  | 1
| 2021-05-03 | [ActivationIntakeApi] -Test Continuous Delivery |  | 2
| 2021-05-10 | [ActivationIntakeApi] -Documentation |  | 1
| 2021-05-17 | [ActivationIntakeApi] -Develop Activate Endpoint |  | 1
| 2021-05-24 | [ActivationIntakeApi] -Develop Get Batch by BatchId Endpoint |  | 2
| 2021-05-31 | [ActivationIntakeApi] -Create Test plans |  | 2
| 2021-06-07 | [ActivationIntakeApi] -Logging |  | 2
| 2021-06-14 | [ActivationIntakeApi] -Backend ready for QA |  | 2
| 2021-06-21 | [ActivationIntakeApi] -Make Public Api |  | 1
| 2021-06-28 | [ActivationIntakeApi] -Add Idp Authentication |  | 1
3rd Quarter | 2021-07-05 | [Activation Processor] - Build Scaffolding project |  | 1
| 2021-07-12 | [Activation Processor] -Test Continuous Integration |  | 2
| 2021-07-19 | [Activation Processor] - Process Low Priority Queue |  | 1
| 2021-07-26 | [Activation Processor] -Test Continuous Delivery |  | 2
| 2021-08-02 | [Activation Processor] - Process High Priority Queue |  | 1
| 2021-08-09 | [Activation Processor] - Move message to Dead Letter queue |  | 1
| 2021-08-16 | [Activation Processor] - Implement retry mechanism |  | 2
| 2021-08-23 | [Activation Processor] - Documentation |  | 1
| 2021-08-30 | [Activation Processor] - Create Test Plan |  | 1
| 2021-09-06 | [Activation Processor] - Ready for QA |  | 1
| 2021-09-13 | [LSS] -Build Scaffolding project |  | 1
| 2021-09-20 | [LSS] -Test Continuous Integration |  | 2
| 2021-09-27 | [LSS] -API that returns no data |  | 1
4th Quarter | 2021-10-04 | [LSS] -Test Continuous Delivery |  | 2
| 2021-10-11 | [LSS] -Documentation |  | 1
| 2021-10-18 | [LSS] -Develop Activate Endpoint |  | 1
| 2021-10-25 | [LSS] -Create Test plans |  | 1
| 2021-11-01 | [LSS] -Logging |  | 1
| 2021-11-08 | [LSS] - Ready for QA |  | 1
| 2021-11-15 | [Activation Processor] -Callout LSS Endpoint |  | 1
| 2021-11-22 | [Activation Processor] - Update Status of Batch Line Items |  | 1
| 2021-11-29 | [Activation Processor] - Update Batch |  | 2
| 2021-12-06 | [Dead Letter Queue Manager] - Update to look at Low Priority Queue |  | 1
| 2021-12-13 | [Dead Letter Queue Manager] - Update to look at High Priority Queue |  | 1
| 2021-12-20 | [Dead Letter Queue Manager] -Create Test plans |  | 1
| 2021-12-27 | [Dead Letter Queue Manager] - Ready for QA |  | 1
|  | Goals | Goals |  | Project Management Guidelines
1st Quarter |  | [BatchStatusApi] - Code Complete | Deployed on Azure |  | Demo every Monday
|  | [BatchStatusApi] - Logging | Angular |  | Weekly planning after demo
|  | [BatchStatusApi] - Health Check | Health Check |  | Consumer/Stakeholder Release every 2 weeks
2nd Quarter |  | [ActivationIntakeApi] - Code Complete |  |  | Tickets represents 4 hours - 3 day block of work
[ActivationIntakeApi] - Logging
[ActivationIntakeApi] - Health Check
3rd Quarter |  | [Activation Processor] - Coding
[Activation Processor] - Logging
[LSS] - Coding
4th Quarter |  | [LSS] - Code Complete
[Activation Processor] - Code Complete
[Dead Letter Queue Manager] - Code Complete